## Slide 1
1 · Presentation
Google Project Management Certificate
Comprehensive Course Review
Foundations of Project Management
Project Initiation · Planning · Execution
Agile and Scrum · Closing and Career Readiness
Google Project Management Certificate

## Slide 2
2 · Foundations
What Is Project Management?
The application of knowledge, skills, tools, and techniques to meet project requirements and achieve the desired outcome.
Key Activities
Planning and organizing
Managing tasks
Budgeting and controlling costs
Ensuring delivery on time and within scope
Why It Matters
Businesses depend on project management to deliver expected outcomes on time and within budget. Without it, projects risk missing goals, overspending, or failing entirely.
Google Project Management Certificate

## Slide 3
3 · Foundations
What Does a Project Manager Actually Do?
Project managers follow a structured process but wear many hats:
Use productivity tools and create processes
Create project plans, schedules, and budgets
Manage and communicate with stakeholders
Identify and manage risks
Guide the team from initiation through closing
Remove obstacles blocking team progress
"A project manager does not do all the work directly. They support the people who do."
Google Project Management Certificate

## Slide 4
4 · Foundations
The Value of a Project Manager
Project managers add value through four core dimensions:
Prioritization
Deciding what the team should focus on first
Delegation
Assigning work to the right people at the right time
Communication
Serving as the main information hub for the team and stakeholders
Organizational Skills
Keeping everyone aligned and moving forward
Project managers shepherd projects from start to finish, serving as guides using impeccable organizational and interpersonal skills every step of the way.
Google Project Management Certificate

## Slide 5
5 · Foundations
Professional Project Management Skills
Core Competencies
Planning and organizing
Managing tasks and priorities
Budget management and cost control
Communication and stakeholder management
Risk identification and mitigation
Leadership and team motivation
Soft Skills That Matter
Negotiation
Empathetic listening
Trust building
Influencing without authority
Google Project Management Certificate

## Slide 6
6 · Foundations
Project Structures and Life Cycles
The Project Life Cycle consists of four phases:
Initiation
Define the project, identify stakeholders, create the project charter
Planning
Develop the project plan, set schedule, identify tasks and milestones
Execution
Carry out the plan, manage the team, track progress
Closing
Formally complete the project, document lessons learned, hand off deliverables
Google Project Management Certificate

## Slide 7
7 · Foundations
Organizational Structure and Company Culture
Types of Organizational Structures
Classic / Functional
Team members report to functional managers, PM has less authority
Matrix
Team members report to both a functional manager and a project manager
Project-based
Team members are dedicated to projects, PM has more authority
Why Culture Matters
Organizational culture is based on shared workplace values. It shows up in how people communicate, make decisions, and work together.
A project that is out of sync with the company's culture is much harder to complete successfully.
Google Project Management Certificate

## Slide 8
8 · Foundations
How Company Culture Affects Project Management
Culture Influences
How decisions are made
How teams communicate
How conflict is handled
How change is accepted
Practical Impact for PMs
Understand who has authority and who needs to be consulted
Adapt communication style to fit the culture
Use the culture's strengths to move the project forward
Recognize when cultural barriers may slow progress and address them proactively
Google Project Management Certificate

## Slide 9
9 · Initiation
Key Parts of Project Initiation
Initiation is where you set the foundation. Key components:
Goals
What you are trying to accomplish
Scope
What is and is not included in the project
Deliverables
The tangible outcomes you will produce
Success Criteria
How you will know the project succeeded
Stakeholders
Everyone who has an interest in the outcome
Resources
Google Project Management Certificate

## Slide 10
10 · Initiation
Setting SMART Goals
Goals must be SMART to be actionable:
Specific
Clearly defined, not vague
Measurable
Has metrics or indicators of success
Attainable
Realistic and achievable
Relevant
Aligned with the broader business objective
Time-bound
Has a defined deadline or timeframe
SMART: "Increase customer satisfaction scores by 15% within 6 months by launching a new follow-up survey system"
Google Project Management Certificate

## Slide 11
11 · Initiation
Scope and Scope Creep
Project Scope
Defines what is included and what is not included in the project.
Scope Creep
Occurs when tasks or features are added to the project without a corresponding change to the timeline, budget, or resources.
How to Prevent Scope Creep
Clearly document what is in scope at the start
Get sign-off from stakeholders on the scope
Have a formal change request process
Push back on additions that are not approved
Scope creep is one of the most common reasons projects go over budget and miss deadlines.
Google Project Management Certificate

## Slide 12
12 · Initiation
Communicating and Working with Stakeholders
Stakeholders are anyone who has an interest in the project outcome, including sponsors, customers, team members, and other departments.
Steps to Manage Stakeholders
Identify all stakeholders early
Understand their interests and influence levels
Create a stakeholder map (RACI chart)
Communicate regularly based on their needs
Involve them at key decision points
RACI Chart
Responsible — does the work
Accountable — owns the outcome
Consulted — provides input
Informed — kept up to date
Google Project Management Certificate

## Slide 13
13 · Planning
The Benefits of Project Planning
The Planning Phase Helps You
Document scope, tasks, milestones, and budget
Set a realistic schedule
Identify risks before they happen
Align the team and stakeholders on expectations
Create a roadmap for execution
What Goes Into a Project Plan
Tasks and milestones
Assigned team members
Documentation and resources
Timeline and deadlines
Lack of planning is one of the top causes of project failure.
Google Project Management Certificate

## Slide 14
14 · Planning
Project Planning for Beginners
The five core elements of a project plan:
Tasks
Activities that need to be completed within a set time
Milestones
Important points that indicate progress or phase completion
People
Who is responsible for what
Documentation
Supporting materials, charters, contracts, requirements
Time
Estimates for each task and an overall schedule
At the center of every project plan is the schedule — your guide for time estimates, milestone tracking, and overall project progress.
Google Project Management Certificate

## Slide 15
15 · Planning
Building a Project Plan
Project plans can be built in a spreadsheet with the following approach:
Review the project charter goals and deliverables
List all tasks associated with each deliverable
Identify milestones within that task list
Estimate time for each task
Assign owners
Track progress continuously
Starting Point
Ask yourself for each deliverable: "What steps do we need to take to achieve this?" Those steps become your tasks.
Analyze emails, old project plans, and stakeholder conversations to uncover additional tasks you may have missed.
Google Project Management Certificate

## Slide 16
16 · Planning
Negotiating with Stakeholders
Strong project plans require buy-in. Key negotiation principles:
Understand what stakeholders truly need, not just what they ask for
Be transparent about constraints (time, budget, scope)
Offer alternatives when you cannot deliver exactly what is requested
Document all agreements to avoid misunderstandings later
Revisit the plan if circumstances change
Empathy is a negotiation tool.
When you understand the stakeholder's underlying goal, you can find creative solutions that work for everyone.
Google Project Management Certificate

## Slide 17
17 · Planning
How to Create a Project Budget
A project budget is the estimated monetary resources needed to achieve the project's goals and objectives.
Budget Components
Labor costs
Materials and supplies
Software and tools
Vendor and contractor fees
Contingency reserves for unexpected costs
Budgeting Steps
Break down costs by milestone and deliverable
Use historical data from similar projects
Get estimates from vendors and team members
Build in a buffer for risk
Google Project Management Certificate

## Slide 18
18 · Planning
Risk Management Basics
Risk is any potential event that could impact the project positively or negatively.
Risk Management Process
Identify risks — brainstorm what could go wrong
Assess likelihood and impact of each risk
Prioritize risks that are both likely and high impact
Create a mitigation plan for top risks
Monitor risks throughout the project
Types of Risks
Schedule risks (delays)
Budget risks (cost overruns)
Scope risks (uncontrolled changes)
Resource risks (people leaving, unavailability)
Google Project Management Certificate

## Slide 19
19 · Planning
Resources and Tools to Manage Your Project
Project Resources
Budget
People
Materials
Common Project Management Tools
Planning
Google Sheets, Excel spreadsheets
Work Management
Asana, Jira, Trello
Communication
Email, Slack, video conferencing
Collaboration
Google Project Management Certificate

## Slide 20
20 · Planning
The Project Communication Plan
A Communication Plan Outlines
Who needs to receive information
What type of information they need
How often they need it
Through which channel (email, meeting, report)
Who is responsible for sending it
Why Communication Plans Matter
Prevents missed updates
Ensures everyone knows what is happening
Reduces confusion and rework
Helps manage stakeholder expectations
Communication is arguably the most important tool in project management. Most project failures involve a communication breakdown.
Google Project Management Certificate

## Slide 21
21 · Planning
Communicate Effectively as a Project Manager
90%
of a PM's time is spent on communication
Effective Communication Is
Clear
Honest
Relevant
Frequent but not excessive (avoid information overload)
Communication Channels to Master
Email
Keep it concise, clear subject lines, appropriate recipients
Meetings
Structured, intentional, agenda-driven
Google Project Management Certificate

## Slide 22
22 · Planning
How to Run a Successful Meeting
The four elements of an effective meeting:
Structured
Starts and ends on time, topics are prioritized, a notetaker is assigned
Intentional
Has a clear purpose and a prepared agenda
Collaborative
Participants are encouraged to contribute
Inclusive
The right people are invited, and everyone has a chance to speak
Send the agenda in advance
Only invite people who need to be there
Assign action items with owners and deadlines
Google Project Management Certificate

## Slide 23
23 · Planning
How to Organize Effective Meetings
Pre-Meeting Preparation
Define the purpose of the meeting
Build an agenda
Share the agenda with attendees beforehand
Book the right time and location (or video link)
During the Meeting
Stick to the agenda
Manage time actively
Record decisions and action items
After the Meeting
Send a summary with action items, owners, and due dates
Follow up on unresolved items
Google Project Management Certificate

## Slide 24
24 · Execution
Project Tracking Methods and Examples
During execution, project managers track progress to ensure the project stays on course.
Gantt Chart
Visual timeline showing tasks, durations, and dependencies
Kanban Board
Visual board with columns for To Do, In Progress, and Done
Burndown Chart
Tracks how much work remains versus time available
Status Reports
Regular written updates shared with stakeholders
The tracking method you choose should match the complexity of the project and the needs of your team and stakeholders.
Google Project Management Certificate

## Slide 25
25 · Execution
Effective Project Management During Execution
During execution, a project manager's focus shifts to:
Keeping the team on track and unblocked
Managing risks as they arise
Maintaining open communication with stakeholders
Monitoring scope, schedule, and budget
Updating the project plan as things change
Key Principle
The project plan is a living document. It should be updated whenever there is a significant change to scope, schedule, or budget, with all changes clearly communicated to the team.
Google Project Management Certificate

## Slide 26
26 · Execution
Leadership vs Management in a Successful Team
Management
Focuses on the logistics — tasks, schedules, budgets, processes
Leadership
Focuses on people — inspiring, motivating, supporting, and empowering the team
Together
The best PMs handle logistics while creating an environment where people do their best work
A team is a group of people who plan, solve problems, make decisions, and review their progress together to achieve a common goal.
Google Project Management Certificate

## Slide 27
27 · Execution
How Project Managers Improve Team Effectiveness
Strong Teams Share
Clear roles and responsibilities
Psychological safety to speak up
Shared understanding of goals
Trust between members
Effective conflict resolution
How PMs Build Effectiveness
Hold regular team meetings and check-ins
Celebrate wins and acknowledge contributions
Address conflict early before it escalates
Remove obstacles blocking team progress
Advocate for the team's needs with upper management
Google Project Management Certificate

## Slide 28
28 · Execution
How Project Managers Can Influence Those Around Them
Influencing is the ability to alter another person's thinking or behaviors without direct authority.
The Four Steps of Effective Influence
Establish Credibility
Show expertise and trustworthiness
Frame for Common Ground
Show how your idea benefits them
Provide Evidence
Use data and examples to support your case
Connect Emotionally
Make the case resonate on a personal level
Influence is a critical skill for project managers who often need to motivate people who do not report to them directly.
Google Project Management Certificate

## Slide 29
29 · Execution
How Project Managers Can Build Customer Satisfaction
Customer satisfaction is a key measure of project success.
Strategies for Strong Customer Relationships
Communicate proactively and transparently
Set realistic expectations from the start
Deliver on your commitments
Involve the customer early and often in decisions
Follow up after delivery to ensure ongoing satisfaction
Soft Skills to Practice
Negotiation
Finding solutions that work for both sides
Empathetic Listening
Understanding what the customer truly wants
Google Project Management Certificate

## Slide 30
30 · Execution
Quality Management and Continuous Improvement
Quality means fulfilling the outlined requirements for the deliverable and meeting or exceeding the needs and expectations of your customer.
The Triple Constraint
Scope
What the project includes
Time
When it will be delivered
Budget
What it will cost
If any one element suffers, overall quality suffers too.
Continuous Improvement
An ongoing effort to improve products, processes, or services. It involves recognizing what needs to change, planning for it, and implementing improvements.
Google Project Management Certificate

## Slide 31
31 · Execution
Understanding Project Success
A project is successful when it achieves its goals, is delivered on time and within budget, and meets quality standards expected by the customer.
Measuring Success
On-time delivery
Within or under budget
Deliverables meet quality criteria
Stakeholder satisfaction
Goals and objectives achieved
Defining Success Criteria
Success criteria must be agreed upon at the beginning of the project. If you wait until the end, stakeholders may disagree about what "success" actually means.
Key Question to Ask
"How will we know when this project is done and successful?"
Google Project Management Certificate

## Slide 32
32 · Execution
Using Data to Tell a Story
Data storytelling transforms raw numbers into meaningful insights that drive decisions and influence stakeholders.
The Six Steps
Define the audience
Collect the right data
Filter by what matters most
Choose the right visualization
Shape the narrative
Deliver the story clearly
Good data storytelling answers:
What happened? Why did it happen? What should we do about it?
Tailor your presentation of data to what your audience cares about and how they make decisions.
Google Project Management Certificate

## Slide 33
33 · Closing
The Steps of the Project Closing Process
Project closing is the formal completion and handoff of the project. Skipping it causes confusion and missed learning opportunities.
Confirm Completion
Ensure all deliverables are done and approved
Release Resources
Free team members and materials for future projects
Lessons Learned
Conduct a retrospective to capture what went well and what could be improved
Archive Documents
Store all project documentation for future reference
Closing formally is not just a formality. It validates all the work done and ensures the customer signs off before resources are dispersed.
Google Project Management Certificate

## Slide 34
34 · Closing
How to Prepare a Project Closeout Report
What to Include
Executive summary
Key accomplishments
Lessons learned
Metrics — budget, schedule, quality
Recommendations for future projects
Purpose of the Closeout Report
It creates a historical record of the project — what was planned vs. what actually happened. Future project managers can use it as a reference, so the same mistakes are not repeated and successful approaches are replicated.
Google Project Management Certificate

## Slide 35
35 · Section Intro
Agile &amp; Scrum
Section 4 of 5 · Course Overview

## Slide 36
36 · Agile
Intro to Agile
Agile is an iterative approach to project management and software development that helps teams deliver value to their customers faster and with fewer headaches.
Agile vs Waterfall
Waterfall is linear — phases are completed sequentially before moving on
Agile is iterative — work is done in short cycles, with constant feedback and adjustment
Agile Values
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
Google Project Management Certificate

## Slide 37
37 · Agile
The Agile Manifesto
Published in 2001 by 17 software developers. The four core values:
Individuals and Interactions
over processes and tools
Working Software
over comprehensive documentation
Customer Collaboration
over contract negotiation
Responding to Change
over following a plan
The left side is valued MORE — but this doesn't mean the right side has no value.
Google Project Management Certificate

## Slide 38
38 · Agile
The 12 Agile Principles (Summary)
The Agile Manifesto contains 12 guiding principles for software development and project delivery:
Early, continuous delivery of valuable software
Welcome changing requirements
Deliver working software frequently
Business and developers collaborate daily
Build projects around motivated individuals
Face-to-face conversation is most effective
Working software is the primary measure of progress
Sustainable development pace
Continuous attention to technical excellence
Simplicity — maximizing work not done
Best architectures emerge from self-organizing teams
Google Project Management Certificate

## Slide 39
39 · Agile
VUCA and Agile Advantages
The VUCA Environment
Volatile
Things change rapidly and unpredictably
Uncertain
The future is difficult to predict
Complex
Many interconnected factors affect decisions
Ambiguous
Situations are unclear and hard to interpret
Why Agile Works in VUCA Environments
Short iterations allow quick course correction
Continuous feedback reveals problems early
Google Project Management Certificate

## Slide 40
40 · Agile
Popular Agile Frameworks and Methodologies
Scrum
Sprint-based framework with defined roles, events, and artifacts. Most popular Agile implementation.
Kanban
Visual workflow system that limits work in progress (WIP) and improves flow.
XP (Extreme Programming)
Software-focused Agile with practices like pair programming and test-driven development.
Lean
Focuses on eliminating waste and maximizing customer value delivery.
Google Project Management Certificate

## Slide 41
41 · Agile
Lean's 5 Core Principles
Lean originated in manufacturing at Toyota and focuses on eliminating waste and delivering maximum customer value.
Define Value
Identify what the customer considers valuable
Map the Value Stream
Chart all steps that create or don't create value
Create Flow
Remove obstacles so work flows smoothly
Establish Pull
Work is pulled based on actual customer demand
Pursue Perfection
Continuously improve to eliminate all waste
Google Project Management Certificate

## Slide 42
42 · Scrum
An Introduction to Scrum
Scrum is a framework within which people can address complex adaptive problems, while productively and creatively delivering products of the highest possible value.
Scrum is Built On
Transparency
Inspection
Adaptation
Scrum Values
Courage · Focus · Commitment · Respect · Openness
Work Structure
Work is done in short, fixed-length iterations called Sprints (1–4 weeks each)
Google Project Management Certificate

## Slide 43
43 · Scrum
The Three Scrum Roles
Each person on a Scrum team has a distinct role with unique responsibilities:
Product Owner
Represents the customer's voice. Owns and prioritizes the Product Backlog. Ensures the team builds the right thing. Decides what gets done in each Sprint.
Scrum Master
Serves the team as a coach. Facilitates Scrum events. Removes impediments. Helps the team improve. Is NOT a traditional project manager.
Development Team
Cross-functional group that builds the product. Self-organizing. Typically 3–9 people. Responsible for delivering a potentially shippable product increment every Sprint.
Google Project Management Certificate

## Slide 44
44 · Scrum
The Five Scrum Events
Each Sprint contains five formal events:
Sprint
1–4 week fixed iteration where the team creates a product increment
Sprint Planning
Team selects work from the backlog and defines the Sprint Goal
Daily Scrum
Daily 15-minute standup: What did you do? What will you do? Any blockers?
Sprint Review
Team demos completed work to stakeholders and gathers feedback
Sprint Retrospective
Team reflects on how to improve processes for the next Sprint
Google Project Management Certificate

## Slide 45
45 · Scrum
The Product Backlog
What Is a Product Backlog?
An ordered list of everything that might be needed in the product. It is the single source of truth for what the team will work on. The Product Owner owns and prioritizes it.
Backlog Items Include
User stories (new features from user perspective)
Bug fixes
Technical improvements
Research and exploration tasks
User Story Format
"As a [type of user], I want to [action], so that [benefit]."
The backlog is never fully done — it evolves as the product and team learn more about customer needs.
Google Project Management Certificate

## Slide 46
46 · Scrum
Backlog Management and Refinement
Backlog refinement (or grooming) is the process of reviewing, ordering, and updating the backlog so it is ready for Sprint Planning.
During Refinement
Review and update backlog items
Clarify acceptance criteria
Estimate the effort required for items
Remove or archive items that are no longer relevant
Adjust priorities based on new information
Story Point Estimation
Story points are a unit of measure for estimating the relative effort required to complete a user story. Common scales include the Fibonacci sequence (1, 2, 3, 5, 8, 13, 21).
A well-refined backlog makes Sprint Planning faster and reduces confusion during execution.
Google Project Management Certificate

## Slide 47
47 · Scrum
Agile Use Cases and Applicability
Agile is not just for software — it can be applied to any project with a high degree of uncertainty or need for flexibility.
Agile Works Best When
Requirements are unclear or likely to change
Speed to market is critical
Customer feedback must be incorporated continuously
The team is small, cross-functional, and self-organizing
Industries Using Agile
Software and technology
Marketing and creative agencies
Healthcare and pharmaceuticals
Financial services and banking
Education and non-profits
Google Project Management Certificate

## Slide 48
48 · Scrum
When to Use Agile or Waterfall
The decision depends on the nature of the project and its environment:
Choose Waterfall When
Requirements are clear and stable
The project is linear with predictable phases
Industry regulations require extensive documentation
Deliverables are fixed (construction, manufacturing)
Choose Agile When
Requirements are unclear or frequently changing
Speed and adaptability are critical
Continuous customer collaboration is possible
The team is comfortable with iteration and ambiguity
Neither approach is universally superior. The best project managers know when to use which, and often blend both.
Google Project Management Certificate

## Slide 49
49 · Scrum
Blending Methods: Hybrid Project Management
Hybrid project management combines elements of both Agile and Waterfall to meet the unique needs of a project.
Common Hybrid Patterns
Waterfall Planning + Agile Execution
Use a waterfall approach to define scope and budget, then execute with Scrum sprints
Phase-gated with Sprints
Use formal phase gates for big decisions but run sprints within each phase
Agile with Fixed Milestones
Use sprints but align them with key delivery dates from a waterfall schedule
The Right Mix
There is no single "right" approach. The best project managers understand both methodologies deeply and adapt their approach to what the project actually needs.
Google Project Management Certificate

## Slide 50
50 · Scrum
Value-Driven Delivery in Agile
Agile teams are obsessed with delivering value — quickly and continuously — to the customer.
Key Concepts
Minimum Viable Product (MVP)
The smallest version of the product that delivers value to the customer
Iterative Delivery
Releasing small, working increments frequently rather than waiting for full completion
Continuous Feedback
Using real customer reactions to guide what gets built next
Why Value-Driven?
In traditional project management, value is delivered only at the end. Agile flips this — you deliver value early and often, which reduces risk and increases customer satisfaction throughout the project.
Google Project Management Certificate

## Slide 51
51 · Scrum
The Value Roadmap
An Agile way of mapping out the product development process. It gives the team direction and prioritizes features that deliver maximum value.
Three Key Components
Product Vision
Why the product exists and where it is headed
Product Roadmap
High-level view of what will be built and when
Release Plan
Schedule for when features will be delivered to users
Value First
The roadmap is not a promise — it is a plan. The Product Owner continuously updates it based on customer feedback, new information, and changing priorities to always ensure the team is building the most valuable things next.
Google Project Management Certificate

## Slide 52
52 · Scrum
Agile Challenges and How to Overcome Them
Common Challenges
Teams resist changing from familiar Waterfall habits
Stakeholders struggle with "no detailed plan upfront"
Lack of customer availability for ongoing feedback
Scope can still creep if backlog prioritization is weak
Misunderstanding of Agile roles and responsibilities
Solutions
Invest in Agile training and coaching for the whole team
Set expectations with stakeholders using roadmaps and release plans
Schedule regular stakeholder demos to gather timely feedback
Use retrospectives to continuously improve team processes
Clarify who owns what with clear role definitions
Google Project Management Certificate

## Slide 53
53 · Scrum
Common Scrum Pitfalls
Team-Level Pitfalls
Treating Daily Scrum as a status meeting to the Scrum Master rather than a team coordination event
Skipping retrospectives when things are "going well"
Overloading Sprints with too much work
Organizational Pitfalls
Scrum Master acting as a traditional manager instead of a servant leader
Stakeholders not attending Sprint Reviews
Changing priorities mid-Sprint without a good reason
Scrum is deceptively simple to understand but difficult to master. The pitfalls above are where most teams get stuck.
Google Project Management Certificate

## Slide 54
54 · Scrum
The Scrum Master as a Coach
The Scrum Master is a servant-leader — they serve the team, not direct it. Their job is to help the team work better, not to assign tasks.
Coaching the Team
Facilitates Scrum events effectively
Removes impediments and obstacles
Teaches Agile principles and Scrum practices
Creates a safe space for team members to experiment and fail
Coaching the Organization
Helps leadership understand Agile principles
Works to remove systemic obstacles
Advocates for the team's needs
Key Distinction
A Scrum Master does NOT assign work. The team self-organizes and pulls their own tasks from the Sprint Backlog.
Google Project Management Certificate

## Slide 55
55 · Agile
The Evolution of Agile and AI in Project Management
How Agile Has Evolved
Scaled Agile frameworks emerged for large organizations (SAFe, LeSS)
Agile spread from software to marketing, HR, education, and government
DevOps and Agile are increasingly combined for end-to-end delivery
Remote and distributed Agile teams are now the norm
AI in Project Management
Predictive risk identification using historical project data
Automated status updates and reporting
Natural language interfaces for backlog management
Resource optimization and scheduling tools
AI assists PMs with data and analysis — but human judgment, communication, and leadership remain irreplaceable.
Google Project Management Certificate

## Slide 56
56 · Career
Finding Your First PM Job
Project management is one of the most sought-after skills across industries. Here is how to get started:
Where to Look
LinkedIn and job boards (Indeed, Glassdoor)
Your network — ask for informational interviews
Internal transfers within your current organization
PM communities and meetup groups
Stand Out as a Candidate
Highlight transferable skills from past roles
Build a portfolio of projects — even personal ones count
Tailor your resume to PM language and responsibilities
Entry Points
Coordinator or associate PM roles
Google Project Management Certificate

## Slide 57
57 · Career
How to Find the Right PM Role for You
Not all PM roles are the same. Understanding the differences helps you find the best fit.
Traditional PM
Construction, manufacturing, or large IT projects. Waterfall-heavy, contract-focused, process-driven.
Technical PM
Works with engineering teams. Requires understanding of software development and technical constraints.
Agile PM / Scrum Master
Focused on facilitating Agile teams. Coaching and servant leadership, not command and control.
Program Manager
Manages multiple related projects simultaneously to achieve a larger strategic goal.
Start by identifying industries you are excited about, then find the PM flavor that fits that environment.
Google Project Management Certificate

## Slide 58
58 · Career
How to Keep Improving as a Project Manager
Continuous Learning
Pursue certifications: PMP, CAPM, PMI-ACP, Scrum certifications
Read PM books and follow industry thought leaders
Attend PM conferences and join professional organizations (PMI)
On-the-Job Growth
Always run project retrospectives and apply the learnings
Seek feedback from team members, stakeholders, and sponsors
Volunteer for challenging projects that stretch your skills
The best project managers are perpetual learners. Every project teaches you something new if you are paying attention.
Google Project Management Certificate

## Slide 59
59 · Summary
Key Takeaways: A Complete Course Summary
Foundation
PM is about delivering value through organized, intentional work
Initiation
Define goals, scope, stakeholders, and success criteria
Planning
Create schedule, budget, risk plan, and communication plan
Execution
Lead the team, track progress, manage risks and stakeholders
Closing
Confirm completion, capture lessons learned, archive docs
Agile & Scrum
Iterative delivery, self-organizing teams, continuous improvement
Google Project Management Certificate

## Slide 60
60 · The End
You Are Ready.
Google Project Management Certificate — Complete
Slides Covered
Major Sections
Projects to Manage
"The successful project manager is one who makes it look easy."
Google Project Management Certificate